## Slide 1
Pefok's PMO
Executive Portfolio Dashboard
Monthly Steering Committee Briefing • [Month, Year]
Prepared by [Programme Director] | [Client] | Confidential

## Slide 2
Portfolio Health at a Glance
As of reporting date
14
Active Projects
+2 vs last month
87%
On-Track Rate
Target: 85%
2.4B
XAF Deployed
Of 3.1B budget
340M
XAF Saved
Waste eliminated YTD
Status Breakdown
9
On Track
3
At Risk
1
Off Track
1
Complete
Pefok's PMO • Confidential
2

## Slide 3
Financial Performance
Budget vs Actual by Workstream
Chart: 
| Infrastructure | Digital | Training | Advisory | Compliance
Budget (M XAF) | 620 | 480 | 320 | 180 | 240
Actual (M XAF) | 580 | 495 | 305 | 175 | 190
Pefok's PMO • Confidential
3

## Slide 4
Top 5 Portfolio Risks
ID
Description
Category
Score
Level
Mitigation
R-001
Vendor delivery slip on core hardware
Schedule
16
Critical
Buffer stock ordered; secondary vendor engaged
R-004
New BEAC compliance mandate mid-project
Compliance
15
Critical
Compliance lead assigned; monthly regulator briefing
R-002
FX volatility on imported components
Financial
12
High
Forward contract locked with treasury
R-005
Legacy integration undocumented APIs
Technical
12
High
Reverse-engineering sprint scheduled
R-003
Key SME departure
Resource
10
High
Cross-training + retention discussion in flight
Pefok's PMO • Confidential
4

## Slide 5
Upcoming Milestones — Next 90 Days
Week 1
Steering Committee sign-off — Digital Core Design
On Track
Week 3
UAT kick-off — Banking Portfolio
On Track
Week 6
Data Center cutover — Infrastructure
At Risk
Week 9
Regulator compliance audit
On Track
Week 12
Portfolio quarterly business review
On Track
Pefok's PMO • Confidential
5

## Slide 6
Decisions Requested & Key Actions
For Steering Committee Decision
• Approve additional 120M XAF for hardware buffer stock
• Endorse revised go-live date (2 weeks slip on Infrastructure)
• Confirm executive sponsor for compliance workstream
Key Actions Owned by PMO
• Publish revised portfolio roadmap by end of week
• Complete SME retention plan with HR
• Deliver compliance training to all workstream leads
• Reset weekly cadence with vendor programme manager
Pefok's PMO • Confidential
6

## Slide 7
Questions & Discussion
info@pefokpmo.com | +237 6 80 74 80 72 | Molyko, Buea, Cameroon