## Schedule
Pefok's PMO
Africa's Premier Project Management Institution
Project Schedule & Gantt
Work breakdown with dependencies and % complete
WBS | Task Name | Owner | Start Date | End Date | Duration (d) | Predecessor | % Complete | Status | Notes
1 | Initiation |  | 2026-01-05 | 2026-01-16 | 10 |  | 100% | Complete
1.1 | Kickoff & charter sign-off | Sponsor | 2026-01-05 | 2026-01-09 | 5 |  | 100% | Complete
1.2 | Stakeholder mapping | PM | 2026-01-12 | 2026-01-16 | 5 | 1.1 | 100% | Complete
2 | Planning |  | 2026-01-19 | 2026-02-13 | 20 | 1 | 80% | In Progress
2.1 | Requirements | BA | 2026-01-19 | 2026-01-30 | 10 | 1.2 | 100% | Complete
2.2 | Design & architecture | Tech Lead | 2026-02-02 | 2026-02-13 | 10 | 2.1 | 60% | In Progress
3 | Execution |  | 2026-02-16 | 2026-05-08 | 60 | 2 | 0% | Not Started
3.1 | Sprint 1 | Team | 2026-02-16 | 2026-02-27 | 10 | 2.2 | 0% | Not Started
3.2 | Sprint 2 | Team | 2026-03-02 | 2026-03-13 | 10 | 3.1 | 0% | Not Started
3.3 | UAT | QA | 2026-04-13 | 2026-05-01 | 15 | 3.2 | 0% | Not Started
4 | Go-Live | PM | 2026-05-04 | 2026-05-08 | 5 | 3 | 0% | Not Started
5 | Closure | PM | 2026-05-11 | 2026-05-22 | 10 | 4 | 0% | Not Started
Pefok's PMO • info@pefokpmo.com ¦ +237 6 80 74 80 72 ¦ Molyko, Buea, Cameroon