## Risk Register
Pefok's PMO
Africa's Premier Project Management Institution
Risk Register
Identify, assess, respond, monitor — updated weekly
Risk ID | Date Raised | Category | Description | Cause | Impact | Probability (1-5) | Impact (1-5) | Score | Response Strategy | Mitigation Action | Owner
R-001 | 2026-01-15 | Schedule | Vendor delay on critical hardware | Global chip shortage | 2-week slip on deployment | 4 | 4 | 16 | Mitigate | Order 30% buffer stock; identify secondary vendor | PM
R-002 | 2026-01-16 | Financial | FX volatility (XAF/USD) | External market | 10% cost overrun on imports | 3 | 4 | 12 | Transfer | Lock forward contract with treasury | CFO
R-003 | 2026-01-18 | Resource | Key SME departure | Retention | Knowledge loss on core module | 2 | 5 | 10 | Mitigate | Cross-train two team members; documentation sprint | PMO
R-004 | 2026-01-20 | Compliance | New BEAC regulatory update | External regulator | Rework of AML workflow | 3 | 5 | 15 | Accept | Assign compliance lead; monthly review | Sponsor
R-005 | 2026-01-22 | Technical | Legacy system integration failure | Undocumented API | Data sync gaps | 3 | 4 | 12 | Mitigate | Prototype integration in Sprint 2 | Tech Lead
Scoring: Probability × Impact = Score. 15+ = Critical, 8-14 = High, 4-7 = Medium, 1-3 = Low
Pefok's PMO • info@pefokpmo.com ¦ +237 6 80 74 80 72 ¦ Molyko, Buea, Cameroon

## Heat Map Reference
Pefok's PMO
Africa's Premier Project Management Institution
Risk Heat Map
Probability × Impact matrix
| Impact 1 | Impact 2 | Impact 3 | Impact 4 | Impact 5
Prob 1 | 1 | 2 | 3 | 4 | 5
Prob 2 | 2 | 4 | 6 | 8 | 10
Prob 3 | 3 | 6 | 9 | 12 | 15
Prob 4 | 4 | 8 | 12 | 16 | 20
Prob 5 | 5 | 10 | 15 | 20 | 25